## Sheet2 (hidden)
Anguilla
Antigua & Barbuda
The Bahamas
Barbados
Belize
Bermuda
British Virgin islands
Cayman Islands
Dominica
Grenada
Guyana
Haiti
Jamaica
Montserrat
St. Kitts & Nevis
St. Lucia
St. Vincent & the Grenadines
Suriname
Trinidad & Tobago
Turks & Caicos Islands

## Workplan FY16-REVISED (hidden)
Work Plan (May 2015 to April 2016): Macroeconomics Programming and Analysis
TA Area | Medium-Term Outcome in the Log Frame | Country | Activity: May 2015 - April 2016 | Inputs: May 2015 - April 2016 (in person-weeks) |  |  |  | Updated Inputs at Nov 1, 2016 (person-weeks - changes in red) |  |  |  | % of updated plan delivered at end-Oct | Delivery status | Milestones | Comments
|  |  |  | IMF HQ | CARTAC resident advisors | ST experts | Total | Updated IMF HQ | Updated LTX | Updated STX | Updated Total
Macroeconomic analysis | Outcomes 1-4 | ECCU | Workshop to assist ECCU Macro Policy Units produce an internally consistent set of macro/fiscal projections | 0.1 | 2 | 2 | 4.1 | 1 | 2 | 2 | 5 | 100 | Delivered on May 6-15 May. | All countries producing internally consistent debt projections | Covered cost for WHD Economist to present over two days
|  | Regional | ICD Course on Macroeconomic Diagnostics | 3 | 1 | 0 | 4 | 3 | 1 | 0 | 4 | 0 | Scheduled for March 14-18 in Suriname. | Workshop deliver on global best practice macro surveillance | Topic changed to Macroeconomic Forecasting. Venue and dates confirmed. | Will happen
| 1. Countries are using macroeconomic forecasts as a basis for annual and medium-term budgets (PI 14(ii), FTE 2.1.2) | SVG | Assist with training staff in a GDP and CPI forecasting framework | 0.1 | 2 | 0 | 2.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled. Reduced by 1 week. | Macro Policy Unit independently producing forecasts |  | May happen
|  | Dominica | Assist with training staff in a GDP and CPI forecasting framework | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 100 | Delivered 28 September - 4 October | Macro Policy Unit independently producing forecasts | The one week Fund staff visit is replaced by this mission
|  | Saint Lucia | Review forecasting framework from previous training session | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 2 | 3.1 | 0 | Not yet scheduled. | Scenarios and risks surrounding baseline forecasts are produced | Mission title will change to assist with producing manuals for Macro Policy Unit | Delete
|  | Grenada | Assist with training staff in a GDP and CPI forecasting framework | 0.1 | 1 | 0 | 1.1 | 0.1 | 2 | 0 | 2.1 | 100 | Delivered July 13-17 | Macro Policy Unit independently producing forecasts | Successful mission so unplanned follow up mission added
|  | Trinidad & Tobago | Advise Ministry of Finance on GDP forecasting methodologies and then assist with implementation | 0.1 | 2 | 3 | 5.1 | 0.1 | 2.5 | 3 | 5.6 | 0.32609 | Delivered as part of IMF mission: Sept 15-25, remainder to be delivered in H2 | MoF of T&T producing multi-year projections with detailed scenarios |  | Should happen
|  | St Kitts | Assist MoF with GDP projection frameworks | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Scheduled Feb 22-26 | Fiscal unit internally producing Macro projections |  | Will happen
|  | Anguilla | Follow up mission to assist with medium-term GDP projections | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled. | producing scenarios around baseline projections |  | Complete
|  | Barbados | Training MoF staff in techniques of Macro projections | 0.1 | 2 | 2 | 4.1 | 0.1 | 1 | 0 | 1.1 | 0.45455 | 2 half days delivered on October 15 and October 20. Fiscal rules mission to occur on Nov-4-16 | MoF undertaking GDP projections | Delivered 2 half days of assistance to MoF. Barbados fiscal rules mission allocated to this. STX have been removed | LTX yes, STX MAYBE
|  | Antigua | Assist with real sector analysis and projections (joint with PFM) | 0.1 | 1 | 0 | 1.1 | 0 | 0 | 0 | 0 | 0 | Cancelled: No commitment from authorities | MoF undertaking GDP projections
| 2. Countries annual budgetary process underpinned by a medium-term macro framework (PI 14(i), FTE 2.1.3) | Turks and Caicos | Follow up revenue forecasting workshop to produce final multi-year projections along with beginning training on MTFF | 0.1 | 0 | 1 | 1.1 | 0.1 | 0 | 1 | 1.1 | 0 | Not yet scheduled | SPDD producing multi-year revenue projections | Leaning on cancelling unless hear back from authorities soon | CANCELLED
|  | Bahamas | Introductory visit and assistance with revenue forecasting | 0.1 | 0 | 1 | 1.1 | 0 | 0 | 0 | 0 | 0 | Cancelled: No commitment from authorities | Revenue forecasts underpinned by macro inputs | Multiple emails sent to FS with no response.
|  | Dominica | Follow up mission to assist with medium-term fiscal framework | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled | Policy unit operating sound internally consistent macroeconomic framework |  | Should happen
|  | SVG | Assist team in the refinement of MTFF | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled | Internally consistent MTFF |  | Should happen
|  | Barbados | Training MoF staff in techniques of revenue projections | 0.1 | 0 | 2 | 2.1 | 0.1 | 0 | 2 | 2.1 | 0 | Not yet scheduled | Revenue projections based on sound Macro inputs |  | May happen
|  | Guyana | Developing a medium-term framework |  |  |  | 0 | 0.1 | 3 | 2 | 5.1 | 9.8039 | Week 1 Scheduled for 16-20 November, 2 further weeks planned but unscheduled | Improved medium-term framework | This unplanned mission was born out of the election | LTX yes, STX MAYBE
|  | Regional | Revenue forecasting and tax policy modelling workshop |  |  |  |  | 3 | 1 | 0 | 4 | 0 | Aiming for late April | Improved medium-term framework | FAD workshop, previously not programmed | Moved to next FY
| 3. Countries adequately reporting on macroeconomic risks and policy (PI 5) | Regional | Workshop - medium term economic and fiscal outlook statements (jointly with CARTAC PFM) | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 100 | Delivered in July | Workshop delivered. Action Plans to implement workshop learnings produced.
|  | Regional | Joint workshop with FS (Shelton) on Macro-Financial linkages | 0.1 | 1 | 1 | 2.1 | [5 empty] | Unscheduled | Modelling capacity built for central bankers to better monitor macro risks to the economy | To discuss with David, Budget dependent
|  | Dominica | Assist with economic reporting | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Not yet scheduled | Further reporting on macroeconomic events |  | Should happen
|  | Saint Lucia | Improving research capacity | 0.1 | 1 | 2 | 3.1 | 0.1 | 1 | 2 | 3.1 | 0 | Scheduled Jan 11-15 | Policy and research papers produced | STX will be Winston Moore | May happen
| 4. Improved macroeconomic and fiscal coordination | Barbados | Provide advice on setting up a macro policy unit | 0.1 | 1 | 0 | 1.1 | 0.1 | 1 | 0 | 1.1 | 0 | Scheduled November 4-16 | Policy unit set up | Rolled into FAD fiscal rules mission | Complete
|  | Regional | Workshop for Financial Secretaries (jointly with CARTAC PFM) | 0.1 | 1 | 0 | 1.1 | [5 empty] | Cancelled due to shifting prioties, another regional workshop added. | Workshop delivered. Action Plans to implement workshop learnings produced.
|  |  |  | 5.1 | 23 | 14 | 42.1
|  |  | Original Plan: | 5.1 | 23 | 14 | 42.1
|  |  | Updated Plan at Nov 1: |  |  |  |  | 8.7 | 23.5 | 14 | 46.2
Delivered at Nov 1:
Percentage of Original Plan:
Percentage of Adjusted Plan:

## GFS
FY18 Work Plan - May 2017 to April 2018: Government Finance Statistics (GFS)
TA Area | Objective | Country | Statistics Dept Outcome Targeted | Activity | May 2017 - April 2018 |  |  | Number of Missions/ Activities | Milestones | Comments | Planned Date | Experts
(in person-days)
[5 empty] | PFTAC resident advisors | ST experts | Total
Government Finance Statistics | 1. Strengthened macroeconomic and financial statistics compilation and dissemination for decision making: compilation methodologies in line with international standards for GFS | Cook Islands | 1.9 Data are compiled and disseminated using appropriate statistical techniques, including to deal with data sources, and/or assessment and validation of intermediate data and statistical outputs. | Refine compilation techniques for using various administrative data sources to reduce statistical discrepancies. | 5 | 0 | 5 | 1 | • Cook Islands National Statistics Office (CINSO) and Crown Accounts Divisions (CAD) to work with departments to reconcile discrepancies for the flows recorded in the accounting system and the asset registers. • The CINSO and CAD to reconcile discrepancies that may exist in the financial balance sheet, the changes in cash balances. [RBM – GO – 9.8] by December 2017. | Improved data for GFS compilation and dissemination. | July 2017 | DeLaBeer
|  |  | 1.12 Higher frequency data has been compiled and disseminated internally and/or to the public. | Compile, review and disseminate data to the IMF Statistics Department. |  |  |  |  | • The CINSO to compile and disseminate consolidated public sector annual data, at least three-year time series. • The CINSO to produce and disseminate quarterly data for the International Financial Statistics (IFS) by December 2017. [RBM – GO – 12.3] | GFS for general government / public sector operations are compiled and disseminated on a annual/quarterly basis.
|  | Fiji | 1.10 Source data are adequate for the compilation of Government Finance Statistics. |  | 12 | 0 | 12 | 1 | • Reconcile grants / transfers between levels of government by July 2017. • Reconcile and validate the loan transactions between general government units and its associated interest expense / revenue cost for elimination by October 2017. • Finalize estimates for local government data breaks in preparation for consolidation by December 2017. [RBM – GO – 10.7] | Source data provide sufficient detail to allow consolidation of GFS for the various levels of the general government. | April 2018 | DeLaBeer
|  |  | 1.12 Higher frequency data has been compiled and disseminated internally and/or to the public. | Compile, review and disseminate data to the IMF Statistics Department. |  |  |  |  | • Produce a monthly GFS report in line with the "State of the Nations Report" for BCG by September 2017 and disseminate for inclusion in the IFS. • Compile and disseminate annual data for BCG (FY 14,15 & 16) by November 2017. • Compile and disseminate consolidated general government annual data by December 2017. [RBM – GO – 12.1 and 12.3] | GFS for general government operations are compiled and disseminated on a annual basis.
|  | FSM | 1.12 Higher frequency data has been compiled and disseminated internally and/or to the public. | Compile, review and disseminate data to the IMF Statistics Department. | 5 | 0 | 5 | 1 | • Compile and disseminate annual data for budgetary central government and state governments for FY16 by November 2017. • Investigate general government elimination entries in preparation for consolidation by April 2018. [RBM – GO – 12.3] | GFS for general government operations are compiled and disseminated on a annual basis. | March 2018 | DeLaBeer
|  | Nauru | 1.5 Data are compiled and disseminated using the coverage and scope of the latest manual/guide. | Compile the institutional unit table for the public sector and investigate source data for GFS compilation purposes. | 12 | 0 | 12 | 1 | • Investigate and complete a list of all institutional units covered for GFS by December 2017. • Investigate all possible data sources for the compilation of GFS by December 2017. [RBM – GO – 5.7, 5.8 and 10.2] | The institutional scope includes all significant central government institutional units and its associated transactions. | September/October 2017 | DeLaBeer
|  |  | 1.9 Data are compiled and disseminated using appropriate statistical techniques, including to deal with data sources, and/or assessment and validation of intermediate data and statistical outputs. | Mapping the national chart of accounts (COA) to GFS. |  |  |  |  | Obtain the National COA for budgetary central government from the Finance Ministry and start the mapping to the GFSM 2014 by December 2017. [RBM – GO – 9.6] | Bridge tables from national source data to GFS classifications have been constructed and are used to compile GFS.
|  | Palau | 1.12 Higher frequency data has been compiled and disseminated internally and/or to the public. | Compile, review and disseminate data to the IMF Statistics Department. | 5 | 0 | 5 | 1 | • Compile and disseminate annual data for budgetary central government for FY16 by November 2017. • Investigate general government elimination entries in preparation for consolidation by April 2018. [RBM – GO – 12.3] | GFS for general government operations are compiled and disseminated on a annual basis. | March 2018 | DeLaBeer
|  | PNG | 1.18 A new data set has been compiled and disseminated internally and/or to the public. | Assist in the verification and revisions of data compiled for GFS. | 12 | 0 | 12 | 1 | • GFS are compiled and disseminated for the budgetary central government by April 2018. • GFS are compiled and disseminated for the general government by April 2019. [RBM – GO – 18.1] | A new set of GFS are compiled and disseminated for the general government as recommended by the GFSM 2014 guidelines. The institutional table need to be updated to cover all statutory bodies by December 2017. | October 2017 | DeLaBeer
|  |  | 1.12 Higher frequency data has been compiled and disseminated internally and/or to the public. | Assist in the verification and revisions of the COA mapping and associated compilation procedures for quarterly reporting. |  |  |  |  | • COA mapping in the Integrated Financial Management System (IFMS) completed by May 2017. Verification and revisions completed by end of December 2017. •Compilation process for completing quarterly GFS reports and provisions for regular revisions completed by April 2018. • GFS for budgetary central government operations are compiled and disseminated on a quarterly basis by January 2019. [RBM – GO – 12.1] | GFS for budgetary central government operations are compiled and disseminated on a monthly (or quarterly) basis.
|  |  | 1.15 Macroeconomic data sets used by policy-makers have been made more intersectorally consistent (reduced discrepancies). | Prepare a reconciliation and include data for the financial balance sheet and public sector data to the monetary statistics and balance of payments. |  |  |  |  | • Consistent reporting of financial assets and liabilities data for consolidation with GFS on a quarterly basis for general government by April 2019. • Initiate a work plan for collecting debt and foreign aid data by June 2018. • Establish a specialized interdepartmental taskforce to coordinate the collection of GFS sources including financing and debt data by December, 2017. [RBM – GO – 15.3 and 15.14] | GFS and debt are consistent or reconcilable with monetary and financial statistics and external sector debt statistics.
|  | RMI | 1.12 Higher frequency data has been compiled and disseminated internally and/or to the public. | Compile, review and disseminate data to the IMF Statistics Department. | 5 | 0 | 5 | 1 | • Compile and disseminate annual data for budgetary central government FY16 by November 2017. • Investigate general government elimination entries in preparation for consolidation by April 2018. [RBM – GO – 12.3] | GFS for general government operations are compiled and disseminated on a annual basis. | March 2018 | DeLaBeer
|  | Samoa | 1.12 Higher frequency data has been compiled and disseminated internally and/or to the public. | Compile, review and disseminate data to the IMF Statistics Department. | 12 | 0 | 12 | 1 | • Compile and disseminate annual data for budgetary central government for FY16 by November 2017. • Investigate general government elimination entries and statistical discrepancies in preparation for consolidation by November 2017. [RBM – GO – 12.3] | GFS for general government operations are compiled and disseminated on a annual basis. | September 2017 | DeLaBeer
|  | Solomon Islands | 1.12 Higher frequency data has been compiled and disseminated internally and/or to the public. | Compile, review and disseminate data to the IMF Statistics Department. | 12 | 0 | 12 | 1 | • Compile and disseminate annual data for budgetary central government for FY16 by November 2017. • Investigate general government elimination entries and statistical discrepancies in preparation for consolidation by April 2018. [RBM – GO – 12.3] | GFS for general government operations are compiled and disseminated on a annual basis. | February 2018 | DeLaBeer
|  | Timor-Leste | 1.9 Data are compiled and disseminated using appropriate statistical techniques, including to deal with data sources, and/or assessment and validation of intermediate data and statistical outputs. | Imbalances using various data sources to compile GFS are investigated and resolved. | 0 | 14 | 14 | 1 | • Review and complete updates between various source systems to resolve discrepancies, e.g. balance sheet transactions by December 2017. • Updates to the COA in ProClarity transparency portal to facilitate GFS compilation completed by December 2017. • Reconciliation of currency and deposits in ProClarity with the monetary statistics released by Central Bank of Timor-Leste be included in GFS quarterly report July 2017. [RBM – GO – 9.8] | Statistical discrepancies and other potential indicators of problems in statistical outputs are investigated. With support of the Information Technology Free balance international team. | April 2018 | Expert
|  | Tonga | 1.5 Data are compiled and disseminated using the coverage and scope of the latest manual/guide. | Complete the institutional unit table for the public sector and investigate source data for GFS compilation purposes. | 12 | 0 | 12 | 1 | • Investigate and complete a list of all institutional units covered for GFS by September 2017. • Investigate all possible data sources for the compilation of GFS by September 2017. [RBM – GO – 5.13, 5.14 and 10.3] | The institutional scope includes all significant general government institutional units and its associated transactions. | June 2017 | DeLaBeer
|  |  | 1.9 Data are compiled and disseminated using appropriate statistical techniques, including to deal with data sources, and/or assessment and validation of intermediate data and statistical outputs. | Mapping the national chart of accounts (COA) to GFS. |  |  |  |  | Obtain the National COA for budgetary central government from the Finance Ministry and start the mapping to the GFSM 2014 by January 2018. [RBM – GO – 9.6] | Bridge tables from national source data to GFS classifications have been constructed and are used to compile GFS.
|  | Tuvalu | 1.9 Data are compiled and disseminated using appropriate statistical techniques, including to deal with data sources, and/or assessment and validation of intermediate data and statistical outputs. | Mapping the national chart of accounts (COA) to GFS. | 12 | 0 | 12 | 1 | Review and update the COA for budgetary central government from the Finance Ministry with mapping it to GFSM 2014 by January 2018. Investigate the options of automating the annual and quarterly reporting through the COA. [RBM – GO – 9.6] | Bridge tables from national source data to GFS classifications have been constructed and are used to compile GFS. | December 2017 | DeLaBeer
|  |  | 1.12 Higher frequency data has been compiled and disseminated internally and/or to the public. | Compile, review and disseminate data to the IMF Statistics Department. |  |  |  |  | • Compile and disseminate annual data for BCG and a time series of at least three years (FY14-FY16) by January 2018. • Compile and disseminate consolidated general government annual data by December 2018. [RBM – GO – 12.3] | GFS for general government operations are compiled and disseminated on a annual basis.
|  | Vanuatu | 1.9 Data are compiled and disseminated using appropriate statistical techniques, including to deal with data sources, and/or assessment and validation of intermediate data and statistical outputs. | Imbalances using various data sources to compile GFS are investigated and resolved. | 0 | 21 | 21 | 1 | • A process be initiated to reconcile currency and deposits and other financial balance sheet transactions causing data imbalances by December 2017. • A reconciliation of transactions in the net investment of nonfinancial assets between various source data causing statistical discrepancies be initiated by December 2017. [RBM – GO – 9.8] | Statistical discrepancies and other potential indicators of problems in statistical outputs are investigated. | August/September 2017 | Expert
|  |  | 1.12 Higher frequency data has been compiled and disseminated internally and/or to the public. | Compile, review and disseminate data to the IMF Statistics Department. |  |  |  |  | • Refine and update the annual and quarterly GFS compilation process in line with GFSM 2014 guidelines and disseminate the data for the IFS by December 2017. • Compile and disseminate annual data for BCG with completing the time series of the last five years (FY12-FY16) by December 2017. • Compile and disseminate consolidated general government annual data by December 2018. [RBM – GO – 12.1 and 12.3] | GFS for general government operations are compiled and disseminated on a annual / quarterly basis.
|  | Regional | Capacity Development in GFS. | GFS methodological training, practical workgroup exercises and country data compilation. | 7 | 17 | 24 | 1 | Workshop delivered and staff trained. | Workshop for selected PFTAC member countries to be held in Fiji. This activity will include a segment of country specific technical assistance to Kiribati. | August 2017 | DeLaBeer/ Expert
|  | Regional | Capacity Development in GFS. | GFS methodological training, practical workgroup exercises and country data compilation. | 9 | 11 | 20 | 1 | Workshop delivered and staff trained. | Sub-regional Workshop for Micronesian members. Venue TBC. | January 2018 | DeLaBeer/ Expert
Real Sector Statistics | 2. Strengthened macroeconomic and financial statistics compilation and dissemination for decision making: accurate and reliable macroeconomic statistics are available
Real Sector Statistics | 3. Strengthened macroeconomic and financial statistics compilation and dissemination for decision making: timely and consistent data are produced and they are readily available, presented clearly, and are well documented.
|  |  | Total Days: |  | 120 | 63 | 183 | 15